AI Dominance Roadmap

A flexible working plan — reorganise rows freely between phases as priorities shift. Check items off as they're completed, assign target dates, and track progress in the final column.

Partnership: Disruptors Media   |   Last reviewed: February 2026   |   Revenue target: $5M by FY2030

How to use this document

| ☐ / ☑ + Strike | Tick the checkbox and strikethrough the text when done. Set Priority to DONE. |
| --- | --- |
| Priority | NOW = this week ¦ HIGH = this month ¦ MED = next 1–3 months ¦ LOW = later ¦ DONE = complete |
| Target Date | Fill in a date or week (e.g. Feb 28, Week of Mar 10). Leave blank if not yet scheduled. |
| Progress / Notes | Running notes, blockers, links, or a quick status (e.g. 'In progress', 'Waiting on Disruptors', '50% done'). |
| Reorganise | This document is a guide, not a rule. Cut rows and paste them into any phase that reflects your current priorities. |

| PHASE 1 0–30 Days · Set the Foundation |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| ✓ | Priority | Action Item | Owner | Target Date | Progress / Notes |
| 🧠 Build the Company Brain (SOPs & Documentation) |  |  |  |  |  |
| ☐ | NOW | List every core process that lives in Jason's head — estimating, lead handling, onboarding, site setup, job completion — and needs to be documented | Jason | — |  |
| ☐ | NOW | Amber records herself handling each lead type (phone, email, website form) to build a call handling training library | Amber | — |  |
| ☐ | HIGH | Ben records key field quality checkpoints and end-of-job checklist for crew onboarding | Ben | — |  |
| ☐ | HIGH | Build first 5 SOPs: (1) Lead Intake, (2) Quote Process, (3) Pre-Job Setup, (4) Site Safety / PPE Check, (5) Job Completion Checklist | Jason + Disruptors | — |  |
| ☐ | HIGH | Choose Company Brain platform (KnowHow, Notion, or Google Doc wiki) and set up the structure | Jason + Disruptors | — |  |
| ☐ | MED | Upload all completed SOPs into the Company Brain so staff can self-serve answers without calling Jason | Amber | — |  |
| 💡 This is the foundation everything else runs on. Without documented processes, AI tools have nothing to work from and new hires take months to ramp up. |  |  |  |  |  |
| ⏱️ Fix Quote Turnaround Time |  |  |  |  |  |
| ☐ | NOW | Set the standard internally: any lead received before 6pm gets a quote by end of next business day | Jason | — |  |
| ☐ | NOW | Work with Disruptors Media to build AI-assisted estimating template v1 | Jason + Disruptors | — |  |
| ☐ | HIGH | Create standardized pricing tiers for the 5 most common job types (bathtub surround drywall, small mold job, asbestos tile floor, pipe insulation, vermiculite by sq ft) | Jason | — |  |
| ☐ | HIGH | Set up Jobber quote reminder — alerts if a quote hasn't been sent within 4 hours of lead entry | Amber | — |  |
| ☐ | MED | Track quote turnaround time weekly — establish a baseline, then reduce it | Amber | — |  |
| 💡 Quote speed is your #1 sales lever right now. Every day of delay is a lead that goes to a competitor. This is the highest-ROI item in Phase 1. |  |  |  |  |  |
| 📞 AI Lead Response & Intake |  |  |  |  |  |
| ☐ | NOW | Deploy after-hours AI call agent with Disruptors Media — answers calls, captures scope, books a callback | Disruptors | — |  |
| ☐ | HIGH | Build pre-estimate AI intake form on website — captures scope, photos, and timeline before Jason or Nelson's site visit | Disruptors | — |  |
| ☐ | HIGH | Set up auto-confirmation text / email from Jobber the moment a lead is entered into the system | Amber | — |  |
| ☐ | HIGH | Create Amber's triage SOP: which lead types she handles independently vs. escalates to Jason or Nelson | Jason + Amber | — |  |
| ☐ | NOW | Audit all lead channels — confirm website forms, email, and text are all routing to Jobber correctly with no gaps | Amber | — |  |
| 💡 A competitor running an AI call agent will capture leads you miss after hours. First-response speed is a competitive advantage. |  |  |  |  |  |
| 🔍 Market & Competitor Intelligence |  |  |  |  |  |
| ☐ | HIGH | Audit Google reviews of key competitors (Mold Pro, RGR, G&M, Certified Asbestos Removal) — identify their most common customer complaints | Jason + Disruptors | — |  |
| ☐ | HIGH | Run a data pull from Xero and Jobber — identify the top 10 most profitable job types by gross margin | Jason | — |  |
| ☐ | MED | Map where leads come from by neighbourhood — use this to guide Disruptors' SEO and ad targeting | Disruptors | — |  |
| ☐ | MED | Document Wise Abatement's key differentiators vs. each competitor — feeds website copy, sales scripts, and ad creative | Jason + Disruptors | — |  |
| 👤 Hiring — Nelson Decision |  |  |  |  |  |
| ☐ | NOW | Finalize decision on Nelson — make the offer or move on | Jason | — |  |
| ☐ | NOW | If Nelson declines: immediately reopen search — do not leave estimating vacant | Jason | — |  |
| ☐ | HIGH | Set up Nelson's onboarding plan using the Company Brain — structured Day 1 through Week 4 learning path | Jason + Ben | — |  |
| 💡 Nelson is a Phase 1 dependency. Without estimating capacity, any lead volume increase from marketing just creates a backlog Jason has to absorb personally. |  |  |  |  |  |

| PHASE 2 30–90 Days · Aggressive Go-To-Market & Team Build |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| ✓ | Priority | Action Item | Owner | Target Date | Progress / Notes |
| 📣 Customer Communication — Make It Unmatchable |  |  |  |  |  |
| ☐ | HIGH | Deploy automated booking confirmation text/email the moment a job is scheduled in Jobber | Amber + Disruptors | — |  |
| ☐ | HIGH | Set up 'crew on the way' automated text — sent on the morning of each job start | Amber + Disruptors | — |  |
| ☐ | HIGH | Build daily project update template Ben can send in under 60 seconds each afternoon | Ben | — |  |
| ☐ | HIGH | Create post-job completion message with a direct link to the Google review request | Amber + Disruptors | — |  |
| ☐ | MED | Build a Wise Abatement post-project guide: mold prevention tips, what to expect after asbestos removal, air quality follow-up | Jason + Disruptors | — |  |
| 💡 Poor communication is the #1 complaint in competitor reviews. Automated touchpoints cost almost nothing and create massive perceived value. |  |  |  |  |  |
| 🌐 SEO & Online Presence (Disruptors Media) |  |  |  |  |  |
| ☐ | NOW | Complete Google Business Profile audit — photos, services, description, Q&A, and hours fully up to date | Disruptors | — |  |
| ☐ | HIGH | Launch 15+ localized SEO landing pages: 'asbestos removal [city]' and 'mold remediation [city]' for Calgary, Okotoks, Cochrane, Airdrie, Chestermere, Red Deer, Drumheller | Disruptors | — |  |
| ☐ | HIGH | Begin publishing 2–3 blog posts per week targeting homeowner questions (what is vermiculite? is mold dangerous? how long does asbestos removal take?) | Disruptors | — |  |
| ☐ | MED | Launch 20 Google Business posts — mix of completed jobs, seasonal tips, FAQs, and before/after content | Disruptors | — |  |
| ☐ | MED | Begin AI search optimization: target Google AI Overviews, ChatGPT, and Perplexity results for Calgary abatement queries | Disruptors | — |  |
| ☐ | MED | Identify top 5 FAQ keywords where competitors are weakest — publish in-depth answer articles | Disruptors | — |  |
| 💡 SEO takes 3–6 months to compound. Starting now means results hit at Month 4–6 — exactly when you want increased lead volume. |  |  |  |  |  |
| ⭐ Review Collection — Target 50+ Google Reviews |  |  |  |  |  |
| ☐ | HIGH | Set up automated Google review request — triggered 24hrs after a job is marked complete in Jobber | Amber + Disruptors | — |  |
| ☐ | HIGH | Manually reach out to last 30 completed customers with a personalized review request from Jason or Ben | Jason / Ben | — |  |
| ☐ | HIGH | Respond to every existing Google review (positive and negative) within 48 hours — Disruptors drafts, Jason approves | Jason (Disruptors drafts) | — |  |
| ☐ | MED | Set milestones: 50 reviews by end of Month 3, 100 reviews by end of Month 6 | Jason | — |  |
| 🏗️ Field Operations — Tighten Up |  |  |  |  |  |
| ☐ | HIGH | Ben implements end-of-day field check-in: crew confirms job status, photos uploaded, and timesheet complete before leaving site | Ben | — |  |
| ☐ | HIGH | Resolve ClockShark timesheet accuracy issues — build a simple SOP with screenshots for field staff | Ben + Amber | — |  |
| ☐ | HIGH | One-on-one with Javi to address engagement drift — set clear written expectations and KPIs | Ben | — |  |
| ☐ | MED | Humberto begins taking on coordinator responsibilities: job prep lists, compliance doc uploads, crew briefings before site start | Ben + Humberto | — |  |
| ☐ | HIGH | Build end-of-job checklist: what gets photographed, uploaded, and confirmed before crew leaves every site | Ben | — |  |
| 💡 Operational consistency is a marketing asset. Every callback or missed update chips away at the 5-star reputation you're building online. |  |  |  |  |  |
| 📋 Nelson Onboarding & Estimating Handoff |  |  |  |  |  |
| ☐ | NOW | Nelson completes 2-week shadowing phase — attends all site visits and quote conversations alongside Jason | Jason + Nelson | — |  |
| ☐ | HIGH | Nelson takes over first estimates independently — Jason reviews before sending for the first 2–4 weeks | Nelson | — |  |
| ☐ | HIGH | Build estimating review process: Nelson submits draft, Jason reviews same day, quote sent within 24 hours of site visit | Jason + Nelson | — |  |
| ☐ | MED | Jason tracks his own hours in operations weekly — benchmark against the Buyback Principle baseline | Jason | — |  |

| PHASE 3 90 Days – 6 Months · Scale the Engine |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| ✓ | Priority | Action Item | Owner | Target Date | Progress / Notes |
| 📐 AI-Powered Estimating Excellence |  |  |  |  |  |
| ☐ | HIGH | Nelson consistently hitting 24-hour quote turnaround — track weekly and address any slippage immediately | Jason | — |  |
| ☐ | HIGH | Launch Disruptors Media custom estimating software v1 — test and refine using real quotes | Nelson + Disruptors | — |  |
| ☐ | HIGH | Build customer-facing pre-visit photo/video capture workflow — clients submit materials before site visit so estimate is 80% complete on arrival | Disruptors + Amber | — |  |
| ☐ | MED | Build pricing calculators for top 8 job types: vermiculite (sq ft + roof pitch + access difficulty), mold (by risk level), asbestos tile, drywall, pipe wrap, etc. | Jason + Disruptors | — |  |
| ☐ | MED | Track win rate by job type and lead source — identify where close rate is highest and double down | Nelson + Amber | — |  |
| 💡 Goal: Nelson quotes 80% of jobs independently with AI template support. Jason touches only complex or large commercial jobs. |  |  |  |  |  |
| 🤝 Referral Program Launch |  |  |  |  |  |
| ☐ | HIGH | Launch homeowner referral program: $150–$200 credit for any customer who refers a completed job | Jason + Disruptors | — |  |
| ☐ | HIGH | Launch GC referral program: priority scheduling + dedicated contact for contractors who send repeat work | Jason | — |  |
| ☐ | MED | Build 30-day post-project follow-up automation asking if customers know anyone who needs Wise Abatement | Disruptors + Amber | — |  |
| ☐ | HIGH | Identify top 10 existing GC relationships and reach out personally about a referral arrangement | Jason | — |  |
| 💡 Referrals close faster and at higher margins than cold leads. Even a simple program can add 15–20% to your lead volume with minimal cost. |  |  |  |  |  |
| 🎬 Video Content & Paid Advertising |  |  |  |  |  |
| ☐ | HIGH | Record 3–5 before/after job walkthrough videos — real Wise Abatement work, narrated by Ben or Jason on-site | Jason / Ben + Disruptors | — |  |
| ☐ | HIGH | Record 2–3 customer testimonial videos — focus on the 'peace of mind' outcome story, not just the service itself | Jason + Disruptors | — |  |
| ☐ | HIGH | Launch first paid ad campaign — Google search ads targeting Calgary asbestos removal and mold remediation keywords | Disruptors | — |  |
| ☐ | MED | Launch retargeting campaigns: anyone who visited the website sees before/after content and testimonials | Disruptors | — |  |
| ☐ | MED | Launch neighbourhood-specific ad campaigns for Okotoks, Cochrane, and Airdrie — highest demand outside Calgary core | Disruptors | — |  |
| 🔄 Systematize the Full Customer Journey |  |  |  |  |  |
| ☐ | HIGH | Full automated communication sequence live end-to-end: booking confirmation → crew ETA → daily update → completion → review request → 30-day check-in | Disruptors + Amber | — |  |
| ☐ | HIGH | Jason's operational hours below 25 hrs/week — track and adjust if not hitting this | Jason | — |  |
| ☐ | HIGH | Ben and Humberto managing all field operations day-to-day without Jason's involvement | Ben + Humberto | — |  |
| ☐ | MED | Nelson handling 80%+ of quotes end-to-end without requiring Jason review | Nelson | — |  |

| PHASE 4 6–12 Months · Dominate the Local Market |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| ✓ | Priority | Action Item | Owner | Target Date | Progress / Notes |
| 🤖 Build the AI Agent Team |  |  |  |  |  |
| ☐ | HIGH | Deploy Admin Agent: handles routine email triage, scheduling follow-ups, and appointment confirmations automatically | Disruptors | — |  |
| ☐ | HIGH | Deploy Estimating Support Agent: pre-qualifies leads, extracts job scope from photos and intake form before Nelson's call | Disruptors | — |  |
| ☐ | MED | Deploy Customer Concierge Agent: answers post-project questions 24/7 via website chat using Company Brain content | Disruptors | — |  |
| ☐ | MED | Deploy Review Agent: triggers review requests and drafts review responses for Jason to approve in one click | Disruptors | — |  |
| ☐ | MED | Track hours saved per week by AI agents vs. previous human labour — report monthly | Jason | — |  |
| 💡 By Month 6, aim to automate 50–60% of what Amber currently handles manually — freeing her for higher-value customer relationship work. |  |  |  |  |  |
| 📍 Own Google's Local Map Pack |  |  |  |  |  |
| ☐ | HIGH | Reach 150+ Google reviews with a 4.8+ average rating — AI-driven follow-up at every job touchpoint | Disruptors + Amber | — |  |
| ☐ | HIGH | Respond to every Google review within 24 hours — especially negative ones (Disruptors drafts, Jason approves) | Jason (Disruptors drafts) | — |  |
| ☐ | MED | Maintain Google Business posting cadence of 3–4 posts per week minimum | Disruptors | — |  |
| ☐ | MED | Add before/after photos from every completed job — uploaded to Google Business monthly by field team | Ben / Humberto | — |  |
| 💡 Top 3 in Google Maps for 'asbestos removal Calgary' is worth more than almost any amount of ad spend — and compounds over time. |  |  |  |  |  |
| 📊 Data-Driven Forecasting |  |  |  |  |  |
| ☐ | MED | Analyze 3 years of Jobber data for seasonal demand patterns — identify peak months for mold vs. asbestos jobs | Jason + Amber | — |  |
| ☐ | MED | Use demand data to pre-book crews 4–6 weeks ahead during peak season — reduce scheduling scrambles | Ben | — |  |
| ☐ | LOW | Test strategic pricing adjustments during peak demand periods (fire season mold remediation, spring renovation season) | Jason | — |  |
| ☐ | MED | Amber and Nelson track lead source performance monthly — identify which channels convert best, cut what doesn't work | Nelson + Amber | — |  |
| 👷 Build the Team for Scale |  |  |  |  |  |
| ☐ | HIGH | Humberto officially promoted to Coordinator — role and pay adjusted to reflect expanded responsibilities | Jason | — |  |
| ☐ | HIGH | Hire 1–2 new field labourers to backfill Humberto's team lead gap and support growth | Jason + Ben | — |  |
| ☐ | HIGH | All field staff trained via Company Brain — new hires reach full competency in 2 weeks instead of 2 months | Ben + Humberto | — |  |
| ☐ | HIGH | Jason's operational hours below 15 hrs/week — working ON the business, not IN it | Jason | — |  |

| PHASE 5 12–24 Months · Outright Market Leadership |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| ✓ | Priority | Action Item | Owner | Target Date | Progress / Notes |
| 🏆 Market Leadership Moves |  |  |  |  |  |
| ☐ | LOW | Identify 1–2 struggling competitors with poor reviews or operational problems — explore acquisition or client-base absorption | Jason | — |  |
| ☐ | LOW | Expand territory campaigns into Red Deer, Drumheller, and Claresholm using postal code demand data from Jobber | Disruptors | — |  |
| ☐ | LOW | Launch dedicated SEO pages, Google listings, and targeted ads for highest-demand outlying markets | Disruptors | — |  |
| ☐ | LOW | Evaluate commercial work expansion — dedicated commercial estimating process and dedicated crew capacity | Jason + Nelson | — |  |
| ☐ | LOW | Explore clean demolition service expansion — systematize the service via Company Brain before launching | Jason | — |  |
| 💡 By Month 12, Wise Abatement should be the obvious first call in Calgary abatement. Phase 5 is about extending that lead and making it permanent. |  |  |  |  |  |
| 💼 Become the Employer of Choice |  |  |  |  |  |
| ☐ | MED | Establish a visible career ladder for all staff: Labourer → Team Lead → Coordinator → Project Manager | Jason | — |  |
| ☐ | MED | Humberto on a formal Project Manager development track — structured mentorship from Jason and Ben | Jason + Ben | — |  |
| ☐ | LOW | Move to bi-weekly or weekly payroll — faster pay cycle than most competitors builds loyalty | Jason + Amber | — |  |
| ☐ | LOW | Wise Abatement recognized in Calgary trades community as the best place to work in abatement | Jason | — |  |
| 💡 The best field crews follow the best-run companies. Your systems become a recruiting advantage over competitors who are still running on chaos. |  |  |  |  |  |
| 💰 The $5M Revenue Target |  |  |  |  |  |
| ☐ | MED | Annual revenue trajectory check — are we on track toward $5M by FY2030? Adjust strategy if not. | Jason | — |  |
| ☐ | MED | Review and adjust pricing annually based on demand data, margin trends, and competitive positioning | Jason | — |  |
| ☐ | LOW | Evaluate Owl & Oak Holdings structure with Manny — is it optimized for the scale we're building toward? | Jason + Manny | — |  |
| ☐ | MED | BTA strategic planning session — present the Vivid Vision and 3-year plan to peer group for structured feedback | Jason | — |  |

Key Metrics — How We'll Know It's Working

Review monthly with Disruptors Media. Update the 'Actual' column at each strategy session.

| SALES & REVENUE |  |  |  |
| --- | --- | --- | --- |
| Metric | Baseline (Now) | Target | Actual (update monthly) |
| Quote turnaround time | 2–14 days | < 24 hours |  |
| Win rate on quotes | ~40% | 55%+ |  |
| Average job value | ~$5,000 | $6,500+ |  |
| Annual revenue | $1.44M (FY2025) | Track toward $5M by FY2030 |  |
| New leads per month | Establish baseline | Grow 20%+ year-over-year |  |
| Lead-to-quote conversion | Track in Jobber | 80%+ |  |

| MARKETING & REPUTATION |  |  |  |
| --- | --- | --- | --- |
| Metric | Baseline (Now) | Target | Actual (update monthly) |
| Google reviews (count) | 101 | 150+ by Month 6 |  |
| Google average rating | 5.0 | 4.8+ |  |
| Website organic traffic | Baseline TBD | 3× within 12 months |  |
| Google Maps ranking | Current position | Top 3 for core Calgary terms |  |
| Review response rate | Ad hoc | 100% within 24 hrs |  |

| OPERATIONS & TEAM |  |  |  |
| --- | --- | --- | --- |
| Metric | Baseline (Now) | Target | Actual (update monthly) |
| Gross profit margin | 45–47% | 47%+ consistently |  |
| Callback / rework rate | Ben tracks | < 2% |  |
| On-time crew start rate | Field KPI | 95%+ |  |
| SOPs documented | Building now | 20+ core processes |  |
| Jason's hours in operations | Too high | < 15 hrs/week by Month 6 |  |

Wise Abatement  ·  AI Dominance Roadmap  ·  Built with Disruptors Media  ·  February 2026

This is a living document. Reprioritize freely. The goal is execution, not adherence to any original phase order.

Disruptors Media Example: https://miro.com/app/board/uXjVJR-_3GI=/